## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: CRIMINAL FACE RECOGNITION SYSTEM | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE : Prof. Vaibhav Yavalkar | [6 empty] | DATE | [6 empty] | 20.04.2023
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks/(D)ays | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Sonal Sonarghare, Harsh Shelke, Meghraj Padwal, SwapnilRathod | 11.01.2023 | 24.01.2023 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Sonal Sonarghare, Harsh Shelke, Meghraj Padval, SwapnilRathod | 24.01.2023 | 07.02.2023 | 2 | 100% | bar: WEEK 3 M to WEEK 5 F
1.3 | Discussing the project topic with the help of paper prototype. | Sonal Sonarghare, Harsh Shelke, SwapnilRathod | 07.02.2023 | 07.02.2023 | 2 D | 100%
1.4 | Designing the Graphical User Interface(GUI) | Sonal Sonarghare, Harsh Shelke, Meghraj Padwal, SwapnilRathod | 07.02.2023 | 06.03.2023 | 4 | 100% | bar: WEEK 5 M to WEEK 8 T
1.5 | Presentation I | Sonal Sonarghare , Harsh Shelke,Meghraj Padwal,Swapnil Rathod | 06.03.2023 | 06.03.2023 | 1 | 100% | bar: WEEK 8 W to WEEK 9 M
2 | Project Design and Implementation
2.1 | Database Design | Harsh Shelke | 20.03.2023 | 01.04.2023 | 2 | 100% | bar: WEEK 9 T to WEEK 10 F
2.2 | Database Connectivity of all modules | Harsh Shelke | 20.03.2023 | 01.04.2023 | 2 | 100% | bar: WEEK 11 M to WEEK 12 F
2.3 | Integration of all modules and Report Writing | Sonal Sonarghare, Meghraj Padwal, SwapnilRathod | 14.03.2023 | 19.04.2023 | 4 | 100% | bar: WEEK 12 M to WEEK 13 W
2.4 | Presentation II | Sonal Sonarghare, Harsh Shelke, Meghraj Padwal, SwapnilRathod | 20.03.2023 | 20.04.2023 | 1 | 100% | bar: WEEK 13 R to WEEK 14 F